## Tasks
Feature/Task | Desciption | Task Type | Started | Ended | Total time | Finished | Is passive | Base Task Types | Boolean values
Create TimeManagement system | Manage time more efficiently by tracking tasks and time taken | Management | 2023-12-27 15:25 | 2023-12-27 20:03 | 0.12639 | YES |  |  | TRUE
Play Test | Play test the game to collect feedback | Playtesting | 2023-12-27 16:45 |  | 0.020833 | NO | TRUE | Coding | FALSE
TimeManagment maintenance | Tweak and update small things for better management | Management | 2023-12-28 08:13 |  | 0.043056 | NO | TRUE | Level design
Make low HP visuals |  | Sprite assets | 2023-12-28 08:57 | 2023-12-28 09:30 | 0.017361 | YES |  | Sprite assets
Implement low HP visuals |  | Coding | 2023-12-28 09:00 | 2023-12-28 16:06 | 0.10972 | YES |  | Audio assets
Make falling sprite + polish sprite sheet |  | Sprite assets | 2023-12-28 09:16 | 2023-12-28 11:24 | 0.052778 | YES |  | Value polishing
Implement new sprite sheet (polish) |  | Coding | 2024-01-01 20:00 | 2024-01-01 22:41 | 0.089583 | YES |  | Management
Improve global structure |  | Coding | 2023-12-28 16:06 |  | 0.036806 | NO | TRUE | Playtesting
Correct small bugs |  | Coding |  |  | Not started | NO | TRUE
Create new levels (level design) |  | Level design | 2024-01-02 22:00 |  | 0.089583 | NO
Correct tilemap collider |  | Coding | 2024-01-02 00:56 |  | Not started | NO

## Sessions track
Motive (task) | Description | Session start | Session end | Session time
Create TimeManagement system |  | 45287.7083 | 45287.8347 | 0.12639
Play Test | Play test Loïs | 45287.6979 | 45287.7083 | 0.010417
TimeManagment maintenance |  | 45288.3444 | 45288.3618 | 0.017361
Play Test | Self play test | 45288.3625 | 45288.3729 | 0.010417
Make low HP visuals |  | 45288.3785 | 45288.3958 | 0.017361
Make falling sprite + polish sprite sheet |  | 45288.3958 | 45288.4132 | 0.017361 | Total hours spend on project
TimeManagment maintenance |  | 45288.4139 | 45288.4396 | 0.025694
Make falling sprite + polish sprite sheet |  | 45288.4396 | 45288.475 | 0.035417 | 0.58611
Implement low HP visuals |  | 45288.4778 | 45288.4889 | 0.011111
Implement low HP visuals |  | 45288.5319 | 45288.5403 | 0.0083333
Implement low HP visuals |  | 45288.5806 | 45288.6708 | 0.090278
Improve global structure | Player instantiation will now be automatic + aura is correctly disabled on main menu | 45288.6715 | 45288.7042 | 0.032639
Improve global structure |  | 45288.734 | 45288.7382 | 0.0041667
Implement new sprite sheet (polish) |  | 45292.8542 | 45292.9437 | 0.089583
Create new levels (level design) |  | 45292.9493 | 45293.0389 | 0.089583
Correct tilemap collider |  | 45293.0396 |  | (Current session) 0h 00m

## Charts
Finished | (Plusieurs éléments)
Étiquettes de lignes | Somme de Total time
Coding | 0.23611
Management | 0.16944
Playtesting | 0.020833
Sprite assets | 0.070139
Level design | 0
Total général | 0.49653